## Sheet1
NUMBER | TASK TITLE | START DATE | DUE WEEK | DURATION | 2021 | [16 empty] | 2022
[5 empty] | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Litterature survery
1.1 | Get familiar with the current state of LT and LA |  |  | 0 | bar: 2021 36 to 2021 39
1.2 | Decide on topic / inquiry question |  |  | 0 | bar: 2021 39
1.3 | Litterature review of articles spesifically relevant to our topic. |  |  | 0 | bar: 2021 40 to 2021 44
1.4 | Review topic |  |  | 0 | bar: 2021 42; 2021 44
1.5 | Define first draft of RQ |  |  | 0 | bar: 2021 44
1.6 | Finalize delivery |  |  | 0
1.7 |  |  |  | 0
2 | Design
2.1 | Make detailed plan for answereing RQ |  |  | 0 | bar: 2021 45
2.2 | Write user stories / sketch architecture / define personalia |  |  | 0 | bar: 2021 46 to 2021 49
2.3 | Create wireframes for implementation |  |  | 0 | bar: 2021 46 to 2021 49
2.4 | Finalize delivery |  |  | 0 | bar: 2021 50
3 | Implement the design
3.1 | Create frontend application |  | 5 | 0 | bar: 2022 2 to 2022 5
3.2 | Find dataset |  | 4 | 0 | bar: 2022 2 to 2022 4
3.3 | Find neural networks |  | 8 | 0 | bar: 2022 5 to 2022 8
3.4 | Find sensor data handling software |  | 8 | 0 | bar: 2022 4 to 2022 8
3.5 | Create backend application |  | 6 | 0 | bar: 2022 2 to 2022 6
3.6 | Implement BKT |  | 6 | 0 | bar: 2022 4 to 2022 6
3.7 | Implement new BKT |  | 8 | bar: 2022 5 to 2022 8
4 | Test implementation
4.1 | NSD application |  | 6 | 0 | bar: 2022 6
4.2 | Test the questions (how many are needed to test mastery, what participants to use) |  | 6 | 0 | bar: 2022 5 to 2022 6
4.3 | Pilot study |  | 9 | 0 | bar: 2022 9
4.4 | Contact participants |  | 9 | 0 | bar: 2022 9
4.5 | Conduct experiment |  | 12 | bar: 2022 12
5 | Analyze the results
5.1 | Analyze the results |  | 16 | 0 | bar: 2022 13 to 2022 16
5.2 |  |  |  | 0
5.3 |  |  |  | 0
5.4 |  |  |  | 0
6 | Write report
6.1 | First draft development choices |  |  | 0 | bar: 2022 6 to 2022 7
6.2 | First draft describe dataset |  |  | 0 | bar: 2022 7
6.3 | First draft new BKT |  |  | 0 | bar: 2022 8
6.4 | First draft experiment description |  |  | 0 | bar: 2022 12 to 2022 13
6.5 | First draft results | bar: 2022 15 to 2022 16
6.6 | Write report |  | 22 | bar: 2022 17 to 2022 23
7 | Revisit phases
7.1 |  |  |  | 0
7.2 |  |  |  | 0
7.3 |  |  |  | 0
7.4 |  |  |  | 0